## Sheet1
High_Level_Risks
Risk ID | Risk Description | Category | Impact | Likelihood | Risk Level | Mitigation Strategy
R1 | Data migration errors or data loss | Technical | High | Medium | High | Phased migration, validation checks
R2 | Integration failures with existing systems | Technical | High | Medium | High | Early integration testing
R3 | Resistance to change from support agents | Change | Medium | High | High | Training & change mgmt plan
R4 | Downtime during platform cutover | Operational | High | Low | Medium | Parallel run & rollback
R5 | Vendor delivery delays | Vendor | Medium | Medium | Medium | Contract SLAs & milestones
R6 | Compliance or data security gaps | Compliance | High | Low | Medium | Security reviews & audits
R7 | Scope creep due to stakeholder requests | Governance | Medium | Medium | Medium | Formal change control
R8 | Budget overrun | Financial | Medium | Low | Low | Cost monitoring & reserves