## Sheet1
RACI_Matrix
Activity / Deliverable | Executive Sponsor (VP CX) | Project Manager | Support Ops Director | IT Lead | Vendor PM | Compliance
Business Case Approval | A | R | C | I | I | I
Project Charter | A | R | C | C | I | I
Requirements Definition | I | A | R | C | C | I
Platform Selection | A | R | C | R | C | C
Data Migration Planning | I | R | C | A | R | C
Integration Development | I | C | I | A | R | C
Testing & Validation | I | R | R | A | R | C
Training & Rollout | I | A | R | C | C | I
Change Requests Approval | A | R | C | C | I | C
Go-Live Decision | A | R | C | C | I | C
Project Closure | A | R | C | I | I | I
Legend:
R = Responsible (does the work)
A = Accountable (final authority)
C = Consulted
I = Informed