## Sheet1
Cost Variance Report
Column Definitions (important)
Cost Category
Baseline Budget (USD)
Actual / Forecast Cost (USD)
Variance (USD)
Variance (%)
RAG Status
Commentary / Action
Cost Category | Baseline Budget (USD) | Actual / Forecast Cost (USD) | Variance (USD) | Variance (%) | RAG | Commentary / Action | Commentary / Action
Platform Licensing | 1200000 | 1200000 | 0 | 0% | 🟢 Green | As contracted | On schedule
Implementation Services | 850000 | 880000 | -30000 | -3.5% | 🟡 Amber | Minor scope adjustment | Minor delay absorbed
System Integration | 600000 | 590000 | 10000 | 0.017 | 🟢 Green | Efficiency gains | Completed as planned
Data Migration | 400000 | 390000 | 10000 | 0.025 | 🟢 Green | Scope refined | Resource optimization
Testing & QA | 250000 | 265000 | -15000 | -6% | 🟡 Amber | Extended UAT | Parallel testing enabled
Training & Change | 300000 | 285000 | 15000 | 0.05 | 🟢 Green | Optimized sessions | Scope adjusted
Project Management | 350000 | 350000 | 0 | 0% | 🟢 Green | As planned | Approved UAT extension
Contingency | 415000 | 350000 | 65000 | 0.157 | 🟢 Green | Partial usage | On track
Total | 4565000 | 4310000 | 255000 | 0.056 | 🟢 Green | Within budget | Go-live approved
Stabilization & Hypercare | W41 | W44 | W41 | W44 | 0 | 🟢 Green | Stable operations
Project Closure | W49 | W52 | W49 | W52 | 0 | 🟢 Green | On track