## Sheet1
KPI Summary
KPI Category | KPI Name | Target | Current Status | RAG | Trend | Owner
Schedule | Schedule Variance (SV) | ≥ 0 | -0.5 weeks | 🟡 Amber | Improving | PM
Schedule | Milestone Completion Rate | 100% | 92% | 🟡 Amber | Stable | PM
Cost | Cost Variance (CV) | ≥ 0 | 0.012 | 🟢 Green | Stable | Finance
Cost | Budget Utilization | ≤ 100% | 98% | 🟢 Green | Stable | Finance
Quality | Open Critical Defects | 0 | 0 | 🟢 Green | Stable | QA Lead
Quality | UAT Pass Rate | ≥ 95% | 96% | 🟢 Green | Improving | QA Lead
Risk | High-Risk Items Open | ≤ 2 | 2 | 🟡 Amber | Stable | PM
Change | Approved Change Requests | ≤ 6 | 4 | 🟢 Green | Stable | PM
Adoption | Training Completion Rate | ≥ 95% | 93% | 🟡 Amber | Improving | Change Lead
Operations | Post Go-Live Escalations | Declining | Low | 🟢 Green | Improving | Ops Lead
KPI Definitions
KPI Name | Definition | Data Source | Review Frequency
Schedule Variance | Difference between planned vs actual schedule | Project Schedule | Weekly
Cost Variance | Planned vs actual cost | Budget Plan | Monthly
UAT Pass Rate | % test cases passed | QA Reports | Weekly
Training Completion | % agents trained | Training Logs | Weekly
High-Risk Items Open | Active high risks | Risk Register | Weekly
Executive Snapshot
Area | Status | Commentary
Schedule | 🟡 Amber | Minor delays absorbed via buffer
Cost | 🟢 Green | Within approved budget
Quality | 🟢 Green | No critical defects
Risk | 🟡 Amber | Migration risks monitored
Readiness | 🟡 Amber | Training nearing completion