## Sheet1
Schedule Variance Report
Column Definitions (important)
Task / Milestone
Baseline Start
Baseline Finish
Actual Start
Actual / Forecast Finish
Variance (Weeks)
Status (RAG)
Commentary / Action
Task / Milestone | Baseline Start | Baseline Finish | Actual Start | Actual / Forecast Finish | Variance (Weeks) | RAG | Commentary / Action
Project Initiation & Approval | W1 | W4 | W1 | W4 | 0 | 🟢 Green | On schedule
Detailed Planning | W5 | W12 | W5 | W13 | -1 | 🟡 Amber | Minor delay absorbed
Platform Vendor Selection | W6 | W10 | W6 | W10 | 0 | 🟢 Green | Completed as planned
Solution Configuration | W13 | W28 | W13 | W29 | -1 | 🟡 Amber | Resource optimization
System Integration | W17 | W30 | W18 | W31 | -1 | 🟡 Amber | Parallel testing enabled
Data Migration | W25 | W32 | W26 | W32 | 0 | 🟢 Green | Scope adjusted
User Acceptance Testing | W31 | W36 | W31 | W37 | -1 | 🟡 Amber | Approved UAT extension
Training & Change Enablement | W33 | W36 | W33 | W36 | 0 | 🟢 Green | On track
Go-Live & Rollout | W39 | W40 | W39 | W40 | 0 | 🟢 Green | Go-live approved
Stabilization & Hypercare | W41 | W44 | W41 | W44 | 0 | 🟢 Green | Stable operations
Project Closure | W49 | W52 | W49 | W52 | 0 | 🟢 Green | On track