## Sheet1
AI-ASSISTED DECISION LOG
Decision ID | Decision Area | Decision Description | AI Tool / Method Used | AI Contribution | Human Judgment / Final Decision | Risk / Limitation Considered | Decision Owner | Outcome
AI-01 | Requirements | Prioritization of support workflows | LLM analysis | Clustered similar requirements | Business priorities overrode AI ordering | AI lacks business context | PM | Final scope approved
AI-02 | Risk | Identification of migration risks | AI pattern analysis | Flagged common migration risks | Risks validated & refined manually | Overgeneralization | PM | Risks added to register
AI-03 | Schedule | High-level schedule sequencing | AI-assisted estimation | Suggested phase durations | Adjusted based on org constraints | Estimation bias | PM | Baseline approved
AI-04 | Cost | Initial cost range estimation | AI benchmarking | Provided industry cost ranges | Finance validated final numbers | Market variance | Finance | Budget approved
AI-05 | Quality | Draft acceptance criteria | AI drafting | Generated initial criteria | Criteria refined with business | Ambiguity risk | QA Lead | Accepted
AI-06 | Change | Impact assessment structuring | AI template suggestion | Structured impact dimensions | Impact values assessed manually | Context loss | PM | Change approved
AI-07 | Communication | Status report framing | AI summarization | Drafted executive summaries | PM edited tone & facts | Misinterpretation | PM | Reports shared
AI-08 | Closure | Lessons learned synthesis | AI summarization | Grouped recurring themes | Final lessons curated | Bias amplification | PM | Lessons logged